## Daily Diary (blank)
DAILY TRAFFIC CONTROL DIARY
Contemporaneous record of temporary traffic control — complete one per day, per closure or operation.
DATE |  |  |  | PROJECT / CONTRACT NO.
COUNTY / ROUTE |  |  |  | WEATHER / TEMP
CONTRACTOR |  |  |  | TC SUPERVISOR (NAME & CERT. NO.)
PHONE
CLOSURE / OPERATION
ROAD NAME & LIMITS (FROM / TO) |  |  |  | DIRECTION
CLOSURE TYPE (LANE / SHOULDER / FULL / MOBILE) |  |  |  | LAYOUT REF. (MUTCD TA / PLAN SHEET)
TIME SET UP |  |  |  | TIME OPENED TO TRAFFIC
TRAFFIC CONTROL DEVICES
DEVICE / SIGN (MUTCD CODE) |  | QTY | LOCATION / STATION |  | TIME SET | TIME REMOVED | CONDITION / NOTES
INSPECTIONS (DRIVE-THROUGH / WALK-THROUGH)
TIME | DAY / NIGHT | DEFICIENCY FOUND |  |  | CORRECTIVE ACTION TAKEN |  | RE-CHECKED
PERSONNEL ON SITE
NAME |  | ROLE (FLAGGER / TCT / SUPERVISOR) |  |  | CERT. NO. |  | HOURS
REMARKS (INCIDENTS, PUBLIC CONTACTS, CHANGES TO SETUP, PHOTOS TAKEN)
TC SUPERVISOR — SIGNATURE / TYPED NAME / DATE |  |  |  | INSPECTOR / AGENCY REPRESENTATIVE / DATE
Free template from PurposeBuilt Systems · purposebuilt.systems/resources/traffic-control-diary-template

## Completed example
DAILY TRAFFIC CONTROL DIARY
Completed example — an ordinary shoulder-closure day, including a deficiency found, corrected and re-checked.
DATE |  |  |  | PROJECT / CONTRACT NO.
06/11/2026 |  |  |  | STP-018-3(74)--2C-77
COUNTY / ROUTE |  |  |  | WEATHER / TEMP
Warren Co. / IA-92 |  |  |  | Clear, 78°F
CONTRACTOR |  |  |  | TC SUPERVISOR (NAME & CERT. NO.)
Midwest Traffic Control, LLC |  |  |  | D. Hollis — TCT #IA-4471
PHONE
515-555-0182
CLOSURE / OPERATION
ROAD NAME & LIMITS (FROM / TO) |  |  |  | DIRECTION
IA-92 from MP 84.2 to MP 85.6 |  |  |  | EB
CLOSURE TYPE (LANE / SHOULDER / FULL / MOBILE) |  |  |  | LAYOUT REF. (MUTCD TA / PLAN SHEET)
Shoulder |  |  |  | MUTCD TA-33 / plan sheet TC-4
TIME SET UP |  |  |  | TIME OPENED TO TRAFFIC
07:05 |  |  |  | 17:40
TRAFFIC CONTROL DEVICES
DEVICE / SIGN (MUTCD CODE) |  | QTY | LOCATION / STATION |  | TIME SET | TIME REMOVED | CONDITION / NOTES
W20-1 Road Work Ahead |  | 2 | MP 83.7 EB / MP 86.1 EB |  | 07:05 | 17:35 | Good
W21-5 Shoulder Closed |  | 1 | MP 84.0 EB |  | 07:10 | 17:35 | Good
G20-2 End Road Work |  | 1 | MP 85.8 EB |  | 07:15 | 17:38 | Good
Channelizing drums |  | 34 | MP 84.2–85.6, 50 ft spacing |  | 07:20 | 17:30 | 1 replaced — see inspections
Type III barricade |  | 2 | MP 84.2 / MP 85.6 shoulder taper |  | 07:25 | 17:30 | Good
Arrow board, caution |  | 1 | MP 84.1 EB shoulder |  | 07:30 | 17:25 | Battery 78% at removal
INSPECTIONS (DRIVE-THROUGH / WALK-THROUGH)
TIME | DAY / NIGHT | DEFICIENCY FOUND |  |  | CORRECTIVE ACTION TAKEN |  | RE-CHECKED
07:45 | Day | None — setup matches TA-33 |  |  | n/a |  | n/a
11:20 | Day | Drum knocked down at MP 84.9 |  |  | Replaced drum, reset spacing |  | 11:35 — OK
15:50 | Day | W20-1 at MP 83.7 rotated by wind |  |  | Re-aimed and re-staked |  | 16:05 — OK
PERSONNEL ON SITE
NAME |  | ROLE (FLAGGER / TCT / SUPERVISOR) |  |  | CERT. NO. |  | HOURS
D. Hollis |  | TC Supervisor |  |  | IA-4471 |  | 10.5
R. Nunez |  | Traffic Control Technician |  |  | IA-5108 |  | 10.0
K. Abbott |  | Flagger |  |  | IA-6620 |  | 8.0
REMARKS (INCIDENTS, PUBLIC CONTACTS, CHANGES TO SETUP, PHOTOS TAKEN)
Paving crew on EB shoulder MP 84.2–85.6 all day. Drum struck by passing vehicle near MP 84.9 at approx. 11:15; no contact reported with workers, no damage beyond the drum. Replaced and re-checked at 11:35. Photos taken of setup at 07:45 and of the replaced drum at 11:35 (6 photos). County inspector J. Prine on site 13:10–13:40.
D. Hollis |  |  | 06/11/2026 | J. Prine |  |  | 06/11/2026
TC SUPERVISOR — SIGNATURE / TYPED NAME / DATE |  |  |  | INSPECTOR / AGENCY REPRESENTATIVE / DATE
Illustrative example — names, project and readings are fictitious. Free template from PurposeBuilt Systems · purposebuilt.systems/resources/traffic-control-diary-template